## Change Request Form
[NASA] Change Request Form
Change Request Number: |  | NASA-CR-076 |  |  | Date: | 2026-06-22
Change Request Status: |  | 3. Ready for Approval |  |  | Prepared By: | K.Pakaporn Ong.
Subject: |  | แก้ไขใบเสนอขาย EN64,EN65,W023
Request Details (Part 1) | Requested by: | K.Athiwat Kanokrattana
| Request Date: | 22 Jun 2026
| Requestor Group: | TRUE |  | FALSE |  | FALSE
| Change Request Detail: | 1.) EN64,EN65,W023 ตัดข้อความในใบเสนอขาย ที่เพิ่งขายเมื่อ กค 2026 บน legacy core 1.1) ฉบับภาษาไทย "สามารถชำระได้เฉพาะเบี้ยประกันภัยปีต่ออายุเท่านั้น" 1.2) ฉบับภาษาอังกฤษ "available for renewal year premium payment only" 2.) W023 แก้ไขข้อความ ตาม OIC
| Reason for Change: | ปรับแก้ไขให้ตรงกับช่องทางที่สามารถชำระได้ในปัจจุบัน และ ตามข้อคิดเห็นของ OIC
| Likelihood of Happening: (select) | Likely (51-75%)
| Expected Benefit: | FALSE | FALSE | FALSE | FALSE | TRUE | FALSE
| Benefits Explanation: | ช่วยให้ผู้เอาประกันภัยได้รับข้อมูลช่องทางการชำระเงินที่ถูกต้องและลดความสับสนในการชำระเบี้ยประกันภัย อีกทั้งยังเป็นการปฏิบัติตามข้อเสนอแนะของ คปภ. อย่างถูกต้องครบถ้วน
Assessment Details (Part 2) | Assessment By: | Kritsada Boonlarp Banharn Swangwarn Pavitree Sriboon Nuttinee Numbunruang Onjira Wongchaicharn
| Impact Analysis | FALSE | TRUE | FALSE | FALSE
| Impact InsureMo / IT surrounding system | FALSE | TRUE | FALSE
|  | Impact InsureMO please consult with IT-core to estimate manpowers and MARS cost required for development or implementation ** Required BU submitted CR /Request to InsureMO team | Impact IT surrounding please consult with IT-owner to estimate manpowers and timeline for development or implementation ** Required BU submitted request to IT-Owner port. | Impact 3rd parties please consult with IT-owner to estimate manpowers and timeline for development or implementation ** Required BU submitted request to IT-Owner port.
| Impact Details: | BA : ปรับแก้ตัวอย่างใบเสนอขาย SA : - UX/UI : - Dev : QA : Create Test Case/Execute Test
| Impact*: | FALSE | FALSE | TRUE | FALSE
| Priority*: | FALSE | FALSE | TRUE | FALSE
BSD/ISD (Please select)
| Effort Details: | TLSMART BA : 0.25 SA : - UX/UI : - Dev : 2 MD QA SIT : 1 MD QA UAT : 1 MD | TL PRO
| Gap List No: |  |  | New / Update:
| Total Mandays: | 4.25 |  | Functional Man-days: | 1.25 | Technical Man-days | 3
| Impact Schedule: |  |  | Remark:
Result (Part 3) | Control Board Decision (PMO, CCB, Council or SC) | 1. Approved (for Implementation) |  | with condition และให้ประเมิน MD ใหม่ของ TL pro เพิ่ม
| Change Request Decision: | 1. Approved (for Implementation) |  | with condition และให้ประเมิน MD ใหม่ของ TL pro เพิ่ม
| Decision Comments: | เนื่องจาก NASA มีแผน re-baseline timeline โดยที่ Defer OL จากเดือน ตค 2026, งาน CR improve product อาจจะต้องไปดำเนินการบน TL PRO plus รบกวน BU action 1. submit CR ที่ TL Pro >> ต้องประเมิน effort IT เพิ่มเติม สำหรับ TL Pro 2. NASA incorporate the new cr เข้า NASA backlog (Tentatvie target date)
Review and Approval
|  |  |  | Name | Date | Signature
TLI PO (Review):
TLI Project Manager (Review):
TLI CCB (Review and Approval):
TLI Council (Review and Approval):
*Note:
Impact
Low Impact |  | Medium Impact |  | High Impact |  | Very High Impact
- No commercial impact |  | - Have commercial impact |  | - Have commercial impact |  | - Have commercial impact
- Minimum effort to update |  | - Up to 5 man-days |  | - Up to 6-10 man-days |  | - More than 10 man-days
- CCB approval via Email |  | - Require CCB and Council Lead Approval in Form |  | - Require CCB and Council Lead Approval in Form |  | - Require CCB and Council Lead Approval in Form
Priority
Low |  |  | Medium |  |  | High
- Minor Change with minimal impact on project success |  |  | - Important change without an immediate crtical impact |  |  | - Critical change that can seriously impact project success
- Can be deferred, solutions don't require immediate changes |  |  | - Impactful if not changes promptly |  |  | - Immediate changes needed
- Minor deviations from the plan |  |  | - Manageable within a reasonable timeframe
Revenue Increase
Please provide quantifiable benefits and rationale
(Ex. Estimated increase in annual revenue XX THB)
Cost Saving
Please provide quantifiable benefits and rationale
(Ex. Reduction in operational expenses XX THB)
Manpower Saving
Please provide quantifiable benefits and rationale
(Ex. Reduction in XX FTEs)
Enhancing Efficiency
Please provide quantifiable benefits and rationale
(Ex. Reduction of XX minutes/process)
Regulatory
Please provide quantifiable benefits and rationale
(Ex. Avoidance of penalties XX THB)
Alignment to Strategy
Please explain contribution to strategic goals
Please estimate the frequency or likelihood of this CR being used by selecting drop down list below
Likelihood of Happening
TLI Business
TLI IT
อื่นๆ (โปรดระบุ)
Low
Low
Please consult with IT to estimate manpowers and cost required for development or implementation.
Technical
Please consult with Legal and Compliance to assess whether this CR required for legal or regulatory compliance.
Legal and Compliance
Please consult with the related BUs to obtain their approval or agrrment with this CR.
Related BUs
Medium
Medium
High
High
Very High
Critical

## Value
BSD
Product
New Business & Underwriting
Policy Servicing (PS)
Claims
BCP
GL
Product Rationalization
Process Change

## Priority and Impact
Priority | Impact
Low | Low Impact
- Minor Change with minimal impact on project success | - No commercial impact
- Can be deferred, solutions don't require immediate changes | - Minimum effort to update
- Minor deviations from the plan | - CCB approval via Email
Medium | Medium Impact
- Important change without an immediate crtical impact | - Have commercial impact
- Impactful if not changes promptly | - Up to 5 man-days
- Manageable within a reasonable timeframe | - Require CCB and Council Lead Approval in Form
High | High Impact
- Critical change that can seriously impact project success | - Have commercial impact
- Immediate changes needed | - Up to 6-10 man-days
- Require CCB and Council Lead Approval in Form
Very High Impact
- Have commercial impact
- More than 10 man-days
- Require CCB and Council Lead Approval in Form